## march 2019
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION REPORT
As of March 31, 2019
CITY OF BAYAWAN
[5 empty] | Location | Total Cost (per Budget Approp) | Target Start Date | Target Completion Date | Project Status |  | No. of Ext., if any | Remarks
|  | Project Code | Year | Program or Project |  |  |  |  | % of Completion | Total Cost Incurred (per Acctg)
1
| 2 |  | 20% ECONOMIC DEVELOPMENT FUND - CURRENT APPROPRIATION
3
| 4 |  | 2019 | Loan Amortization |  | 58000000 |  |  |  | 39813056.19 |  | Obligation per SAAOB
Land
|  |  | 2019 | Lot Acquisition for Dita Relocation |  | 5000000
|  |  | 2019 | Lot Acquisition for Road Right of Way (Villreal) |  | 500000
|  |  | 2019 | Lot Acquisition for Agricultural Development Center (Tan-ayan) |  | 2500000
Road Networks
|  |  | 2019 | Wayang Access Road Development |  | 20000000
|  |  | 2019 | Construction of Ondol-Napit-an FMR |  | 20000000
|  |  | 2019 | Concreting of Access Road from National Highway to Palongpong Agricultural Development Center |  | 9000000
|  |  | 2019 | Improvement of Road Leading to Danapa Inland Aquaculture Facility |  | 2000000
|  |  | 2019 | Concreting of Perimeter Road at BCWMEC |  | 2000000
|  |  | 2019 | Concreting of Urban Roads with Drainage System (Gomez St.) |  | 3000000
Flood Control Systems
|  |  | 2019 | Construction of Drainage Canal at Magsulay Agricultural Development Center |  | 400000
|  |  | 2019 | Concreting of Drainage Canals at Barangay Proper, San Isidro |  | 400000
Water Supply Systems
|  |  | 2019 | Construction & Installation of Water Supply Systems for Barangays Malabugas, San Roque, Minaba, San Miguel and Tayawan |  | 27000000
Power Supply Systems
|  |  | 2019 | Electrification Project at Purok Ipil-Ipil, San Roque |  | 600000
Other Infrastructures Assets
|  |  | 2019 | Establishment of Cotton Ginnery and Spinning Center |  | 10000000
|  |  | 2019 | Site Improvement of Bayawan City Waste Management & Ecology Center |  | 9300000
School Buildings
|  |  | 2019 | Construction of Day Care Center, Barangay San Miguel |  | 400000
Markets
|  |  | 2019 | Construction of Public Market Stalls in Omod, Maninihon (Phase 1) |  | 1678571.43
Other Structures
|  |  | 2019 | Completion of Lapay Multi-Purpose Pavement |  | 360000
|  |  | 2019 | Construction of Concrete Fence of Minaba Elementary School |  | 500000
|  |  | 2019 | Construction of Concrete Fence of Canabuan Elementary School |  | 500000
|  |  | 2019 | Construction of Concrete Fence of Minaba High School |  | 678571.43
|  |  | 2019 | Construction of Barangay Multi-Purpose Building, Nangka |  | 1678571.43
|  |  | 2019 | Construction of 2-Storey Multi-Purpose Building, Barangay Poblacion |  | 1678571.43
|  |  | 2019 | Construction of Concrete Fence of Bolirocon Elementary School, San Isidro |  | 278571.43
|  |  | 2019 | Construction of Multi-Purpose Building, Barangay San Isidro (Phase 3) |  | 1000000
|  |  | 2019 | Construction of Perimeter Fence at San Roque Elementary School |  | 578571.43
|  |  | 2019 | Construction of Barangay Multi-Purpose Building, Tinago (Phase 3) |  | 1678571.43
|  |  | 2019 | Establishment of Agricultural Research Center |  | 10877134.99
Other Transportation Equipment
|  |  | 2019 | Purchase of Garbage Compactor Truck |  | 5000000
|  |  | 2019 | Purchase of Vacuum Declogger Truck |  | 2000000
Breeding Stocks
|  |  | 2019 | Purchase of Livestock Breeding Stocks |  | 2000000
| 87 |  |  | TOTAL EDF - CURRENT APPROPRIATION |  | 200587135 |  |  |  | 39813056.19
| 90 |  | 20% ECONOMIC DEVELOPMENT FUND - CONTINUING APPROPRIATION
91
| 92 |  |  | CAPITAL OUTLAY
| 93 |  |  | 3918 - Purchase, Construction and Improvement of Government Facilities
94
| 95 | ngas 2 |  | Environmental Sanitation Program: |  | 0
| 96 |  | 2004 | 1. Sanitary Landfill (Land Acquisition) 2004 | Maninihon | 1000000 |  |  |  | 8311
no obligation | 97 |  | 2001 | 2. Sanitary Landfill - Dumpsite Acquisition 2001 | Maninihon | 500000 |  |  |  | 0
264-004-11-10-G0021 | 99 |  | 2011 | Renovation of BDH Canteen | BDH, Ubos | 114000 | 2011-06-01 | 2012-12-31 | 100% | 80418 |  | Completed
266-003-11-05-G0009 | 100 | 10710020-006-0003 | 2011 | Const. of Hanging Bridge at Sitio Tiki, Kalumboyan (Phase 3) | Kalumboyan | 700000 | 2011-07-01 |  | 37% | 546410.34 |  | Temporarily Stopped - heavily damaged by typhoon
264-003-1603-G0021 | 103 | 10710030-005-0002 | 2012 | Construction of Slaughterhouse | Suba | 10000000 | 2016-09-16 | 2018-03-31 | 100% | 7807670.74 |  | 100% Completed as per POW: Materials delivered- 75%; cancelled- 25%(rectangular tube, CHB, plywood, floor/wall tiles, blind rivets, drill bits, electrical materials & steel plate - for re-P.R. (100-17-01-023 - delivered-100%)]
264-009-13-04-G0429 | 104 | *10710030-030-0023 | 2012 | Improvement of Bayawan City Boulevard (Landscaping fronting GK Village) | Villareal | 535115.83 | 2013-08-01 | 2014-03-15 | 100% | 495907.52 |  | Completed
264-009-13-03-G0424 | 105 | *10710030-030-0021 | 2013 | Construction of Sports Center and Children's Playground, Phase 3 | Suba | 3000000 | 2013-03-18 | 2015-05-30 | 100% | 2661470.08 |  | Completed
264-009-13-07-G0437/267-004-13-06-G0003 | 106 | *10710030-030-0024 | 2013 | Construction of Covered Court at BCsTEC, Phase II | Cabcabon, Banga | 3008100 | 2013-10-01 | 2017-06-30 | 100% | 2783489.42 |  | Completed
264-009-13-09-G0445 | 107 | 10710030-030-0025 | 2013 | Rehabilitation of GK Septic Tanks | Villareal | 3104400 | 2013-11-18 |  |  | 77968.68 |  | Pending: : Due to sub-standard materials delivered; Materials delivered- 3%; for Delivery- 97% (Fiber Glass septic Tank)
269-001-1511-G0039 | 110 | *10710020-002-0036 | 2013 | Improvement of Water System for 21 Rural Barangays | Bayawan City | 568710 | 2016-07-01 | 2017-07-31 | 100% | 468013.78 |  | Completed
271-002-14-05-G0027 | 111 | *10710020-007-0002 | 2013 | Construction of Drainage Canal with Cover Along City Streets | Bayawan City | 606779.6 | 2014-06-02 | 2014-11-30 | 100% | 544360.59 |  | Completed
| 112 | 0 | 2013 | Fabrication of Distillation Chamber for Essential Oil Production | Banga | 150000 |  |  |  | 0
266-001-14-05-g0313 | 118 | *10710020-001-0011 | 2014 | Construction of Bayawan City Boulevard / Phase 2 | Bayawan City | 1000000 | 2014-08-16 | 2014-10-30 | 100% | 936750.81 |  | Completed
264-009-14-10-e14-475 | 119 | *10710030-030-0031 | 2014 | Const. of Motorpool Building, Phase 1, Cabcabon | Cabcabon, Banga | 8483700 | 2015-07-06 | 09/31/17 | 100% | 7911686.98 |  | Completed
| 120 |  |  | Construction & Heavy Equipment
| 121 | per saaob | 2014 | Major Repair - Construction & Heavy Equipment | Motorpool Area | 10000000 | 2014-06-11 |  | 22.43% | 2242763 |  | Obligation per SAAOB
| 122 |  |  | Roads, Highways & Bridges |  | 0
266-001-1603-G0360 | 129 | 10710020-001-0039 | 2014 | Road Surfacing from Sitio Binanigan to Sitio Guintana-an, Brgy. Tayawan, Phase 1 | Tayawan | 500000 | 2016-03-16 |  | 75% | 137164.48 |  | Temporary stopped; (need to look other quarry source, road not yet passable, Lack of Backhoe available)
130
| 131 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits |  | 0
269-001-14-07-G0036 | 132 | *10710020-002-0025 | 2014 | Construction of Water System-Crusher Kalumboyan | Kalumboyan | 212800 | 2015-06-01 | 2016-06-30 | 100% | 182355.32 |  | Completed
| 134 |  |  | Other Structures
264-009-1510-G0520 | 136 | 10710030-030-0058 | 2015 | Construction of Evacuation Center, Brgy. San Miguel | San Miguel | 800000 | 2016-02-01 |  | 80% | 542345.16 |  | Temporary stopped; Materials delivered- 63%;for delivery-8%; re-canvas -29% [G.I. PIPE, 50mmØ - waived]
264-009-1601-G0524 | 137 | *10710030-030-0059 | 2015 | Construction of Portable Toilet | Bayawan City | 770000 | 2016-01-15 | 2018-03-31 | 100% | 542234.04 |  | Completed
264-009-1601-G0526 | 138 | 10710010-002-0003 | 2015 | Const. of GK Village Perimeter Fence | Villareal | 2000000 | 2016-10-01 |  | 65% | 1716184.88 |  | On-Going: Materials delivered-90% for delivery-10%
| 144 |  |  | Construction & Heavy Equipment
| 145 | no obligation | 2015 | Purchase of Various Heavy Equipment |  | 3476406.99 |  |  |  | 0
| 146 |  |  | Roads, Highways & Bridges
266-001-1504-G0335 | 151 | *10710020-001-0019 | 2015 | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 2 | Bayawan City | 500000 | 2015-06-01 | 2015-06-30 | 100% | 457677.34 |  | Completed
266-001-1502-g0319 | 152 | 10710020-001-0013 | 2015 | Construction of Gomez Street Extension | Bayawan City | 3000000 | 2016-03-16 | 2018-06-30 | 100% | 1148517.88 |  | Physically Completed
266-001-1502-g0326 | 153 | *10710020-001-0016 | 2015 | Concreting of Road Shoulder of National Highway Fronting BNHS, | Bayawan City | 3000000 | 2016-02-09 | 2017-01-15 | 100% | 2935348.39 |  | Completed
266-001-1504-g0330 | 154 | *10710020-001-0017 | 2015 | Construction of Access Road at Bayawan East, | Bayawan City | 2053659.56 | 2015-04-01 | 2016-03-15 | 100% | 1967337.73 |  | Completed
266-001-1603-G0361 | 155 | 10710020-001-0040 | 2015 | Road Surfacing of Sitio Hag-um and Sitio Mambunot, Brgy. Tayawan, Phase 1 | Tayawan, Bayawan City | 500000 | 2016-03-16 |  | 30% | 150690.31 |  | Temporary stop; (need to look other quarry source, road not yet passable, Lack of Backhoe available)
266-001-1509-G0343 | 156 | *10710020-001-0022 | 2015 | Rehabilitation of FMR at Sitio Tubod, Brgy. Tabuan | Tubod, Tabuan | 100000 | 2015-10-01 | 2016-03-15 | 100% | 56654.12 |  | Completed
266-001-1509-g0338 | 157 | *10710020-001-0021 | 2015 | Rehabilitation of Pulangyuta-Lapay FMR | Bayawan City | 2014400 | 2015-09-16 | 2017-03-31 | 100% | 2008455.26 |  | Completed
163
164
| 165 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits
269-001-1603-G0039 | 166 | 10710020-002-0037 | 2015 | Water System Development @ Sitio Camague to Cabiguhan, Brgy Banaybanay | Banaybanay | 303389.8 | 2017-02-16 |  | 50% | 206913.03 |  | Pending: Declared site has no water source; Materials completely delivered
| 177 |  |  | Hospital & Health Centers
264-004-1603-G0031 | 178 | 10710030-003-0001 | 2016 | Rehabilitation of Health Center & Const. of Lying-in Facility, Brgy. Poblacion, Phase 2 | Poblacion | 500000 | 2016-09-16 | 2017-06-30 | 100% | 320188.77 |  | Physically Completed: Materials delivered-85%; for delivery-15% [signage]
| 180 |  |  | Electrification, Power & Energy Structures
264-005-1611-G0058 | 181 | 10710030-006-0010 | 2016 | Installation of Electrical System (Sitio Napit-an, Brgy Maninihon & Zamora Streets, Brgy. Suba) - | Suba | 1500000 | 2016-11-15 | 2018-08-31 | 100% | 1439250.62 |  | Physically Completed, For COC issuance
| 182 | *264-005-1606-G0056 | 2016 | Purchase of Transforments & Primary Metering @ New Gov't. Center | Banga | 2545000 | 2016-11-24 | 2016-11-29 | 100% | 2540000 |  | Completed
264-005-1606-G0055 | 183 | 10710030-006-0009 | 2016 | Installation of Secondary Line Feeder @ New Gov't. Center | Banga | 800000 | 2016-02-13 | 2018-07-15 | 100% | 669519.56 |  | Physically Completed: Materials delivered- 99%; for delivery-1% [marine plywood & round washer]
266-004-1603-g0055 | 184 | 10710020-001-0044 | 2016 | Establishment of Street Lighting Facilities - 2016 | Var. Brgys. | 400000 |  |  |  | 314630 |  | For Implementation: Materials delivered-90%; rebid-10% [g.i. pipe, balast & switch
266-004-1607-G0056 | 185 | *10710020-001-0065 | 2016 | Installation of Street Lightings at Brgy Proper, Villasol | Villasol | 140000 | 2017-10-02 | 2017-10-30 | 100% | 132852.6 |  | Completed
| 186 |  |  | Other Structures
264-009-1607-G0553 | 187 | 10710030-002-0010 | 2016 | Construction of Day Care Centers in Nangka and Napit-an/Rehabilitation of Day Care Centers in Minaba, Narra, Purok 4 Tayawan | Nangka, Napit-an, Minaba, Narra, Tayawan | 2000000 | 2017-06-01 |  | 51.7% | 1365061.08 |  | Consolidated Materials delivered- 72%; rebid- 28% [CHB, plywood, and lumber]
264-009-1607-g0548 | 188 | 10710030-030-0079 | 2016 | Improvement of CICL Center Faciltities | Banga | 975000 | 2017-11-16 | 2019-02-28 | 95% | 764122.65 |  | Consolidated Materials delivered- 59%; for delivery- 14% [cement] ; rebid- 27% [plywood & lumber]
264-009-1607-g0550 | 189 | *10710030-030-0081 | 2016 | Completion of Paglaum Center at Cabcabon | Cabcabon | 500000 | 2016-10-16 | 2018-05-31 | 100% | 352817.03 |  | Completed
264-009-1603-G0533 | 190 | 10710030-030-0069 | 2016 | Completion of Women's Multi-purpose Center | Boyco | 1000000 | 2016-12-01 | 2018-11-30 | 100% | 806442.64 |  | Physically Completed
264-009-1607-g0547 | 191 | 10710030-030-0078 | 2016 | Construction of Women's Detention Cell | Banga | 400000 |  |  |  | 224575.96 |  | Consolidated Materials delivered, 82%; rebid- 18% [CHB, lumber & plywood]
264-009-1603-G0538 | 192 | 10710030-030-0067 | 2016 | Construction of Women's Facilities in Evacuation Center | Var. Brgys | 200000 |  |  |  | 100815.93 |  | For Implementation: Materials delivered-96%; rebid- 4% [lumber]
264-002-1603-G0078 | 194 | *10710030-002-0009 | 2016 | Construction of Day Care Center at Brgy. Proper, Brgy,. San Miguel | San Miguel | 500000 | 2016-08-16 | 2017-05-31 | 100% | 433707.5 |  | Completed
264-009-1603-G0540 | 196 | 10710030-030-0073 | 2016 | Const. of Bleachers & CRs @ Existing Gyms for evacuation (Tinago, Boyco, Suba,Poblacion, Banga, Malabugas, Villareal, BNHS) | Various Brgys | 6000000 |  | 2019-02-28 | 95.75% | 5081521.96 |  | Materials delivered- 10%; for delivery-67%; rebid-23%
| 197 |  |  | a. Tinago |  |  |  |  | 99% |  |  | On-going
| 198 |  |  | b. Boyco |  |  |  |  | 90% |  |  | Pending: Due to DPWH Allocation
| 199 |  |  | c. Suba |  |  |  |  | 99% |  |  | On-going
| 200 |  |  | d. Poblacion |  |  |  |  | 99% |  |  | pending
| 201 |  |  | e. Banga |  |  |  |  | 86% |  |  | pending
| 202 |  |  | f. Malabugas |  |  |  |  | 95% |  |  | On-going
| 203 |  |  | g.Villareal |  |  |  |  | 99% |  |  | pending
| 204 |  |  | h. BNHS |  |  |  |  | 99% |  |  | pending
264-009-1606-G0544 | 205 | 10710030-030-0076 | 2016 | Improvement of Agricultural Dev. Ctr. (ADC), Cansumalig, Phase 2 | Cansumalig | 400000 | 2017-06-01 | 2018-06-30 | 100% | 341523.95
264-009-1604-G0541 | 207 | 10710030-030-0074 | 2016 | Const. of Comfort Rooms in 13 Evacuation Ctrs. | Var Brgys | 1054174.83 |  | 2018-02-28 | 98.38% | 1056488.39 |  | Materials delivered- 45%; for delivery-29%; rebid- 26%
| 208 |  |  | a. Banga Central School |  |  |  |  | 100%
| 209 |  |  | b. BCSTEC Elementary & Highschool |  |  |  |  | 100%
| 210 |  |  | c. Malabugas Highschool |  |  |  |  | 100%
| 211 |  |  | d. Nangka Elementary School |  |  |  |  | 91% |  |  | on-going
| 212 |  |  | e. Guisocon Elementary School |  |  |  |  | 100% |  |  | Physically Completed
| 213 |  |  | f. Atilano Cabangal Memorial Highschool |  |  |  |  | 100% |  |  | Physically Completed
| 214 |  |  | g. Tavera Elementary School |  |  |  |  | 100%
| 215 |  |  | h. Dean Felix Gaudiel Memorial Elementary School |  |  |  |  | 100%
| 216 |  |  | i. H. Bido Jordan Elementary School |  |  |  |  | 100%
| 217 |  |  | j. Bayawan National Highschool |  |  |  |  | 100%
| 218 |  |  | k. Maninihon Elementary & Highschool |  |  |  |  | 95% |  |  | on-going
| 219 |  |  | l. H. Bido Jordan Highschool School |  |  |  |  | 100%
| 220 |  |  | m. SLGTMES |  |  |  |  | 50% |  |  | on-going
264-009-1603-G0536 | 221 | *10710030-030-0072 | 2016 | Improvement of Covered Court/Evacuation Ctr., Bry. Banga | Banga | 500000 | 2016-10-16 | 2017-06-30 | 100% | 435324.88 |  | Completed
264-009-1603-G0535 | 223 | 10710030-030-0071 | 2016 | Const. of Evacuation Ctr., Brgy. San Roque | San Roque | 500000 | 2017-06-16 |  | 79% | 500000 |  | Materials delivered-71%; for delivery-29% [def./angle bar, mesh wire & plywood]
264-009-1603-G0534 | 224 | *10710030-030-0070 | 2016 | Const. of Covered Court/Evacuation Ctr., Bry. Suba | Suba | 500000 | 2016-12-16 | 2017-05-31 | 100% | 454964.53 |  | Completed
264-009-1608-G0557 | 225 | 10710030-030-0082 | 2016 | Const. of Multi-Purpose Bldg. for Evacuation Ctr., Brgy Villareal | Villareal | 500000 | 2017-05-01 | 2018-11-30 | 100% | 431575.23 |  | Physically Completed
| 228 | *10710020-002-0043 | 2016 | Const. of Rain Collector at Brgy. San Isidro | San Isidro | 150000 | 2017-12-16 | 2018-05-31 | 100% | 137210.67 |  | Completed
| 229 | 0 | 2016 | Fish Farm Development Program |  | 900000 |  |  |  | 0
264-009-1701-G0560 | 230 | 10710030-030-0084 | 2016 | Establishment of Youth Development Center |  | 5000000 | 2017-06-15 | 2018-09-01 | 100% | 4000896.6 |  | Physically Completed
| 231 | 10710030-003-0009 | 2016 | Renovation of the Integrated Business Center(IBC) Building | Villareal | 8000000 | 2018-04-27 | 2019-02-28 | 96% | 6223227.42 |  | On-Going: Contract
264-009-1703-G0564 | 232 | 10710030-030-0086 | 2016 | Pilot Livestock Silage Stocking Project |  | 2000000 |  |  |  | 1391084 |  | For Implementation: Delivered - 96%: re-ad - 4%
| 233 | 0 | 2016 | LGU Counterpart for the Construction of Sports Complex |  | 15000000 |  |  |  | 0
264-009-1708-g0577 | 234 | *10710030-004-0005 | 2016 | Establishment of Bayawan Farmers' Market in Dumaguete |  | 5000000 | 2018-02-05 | 2018-10-31 | 100% | 4994489.13 |  | Completed
| 235 |  |  | Agricultural, Fishery & Forestry Equipment
| 236 | per saaob | 2016 | Purchase of Agricultural & Forestry Equipment and Implements |  | 8800000 |  | 2018-12-31 | 100% | 8400000 |  | Obligation per SAAOB
| 237 |  |  | Technical & Scientific equipment
| 238 | no obligation |  | Purchase of Digital Weighing Scale |  | 250000 |  |  |  | 0
| 239 |  |  | Roads,Highways & Bridges
266-001-1601-G0353 | 243 | *10710020-001-0031 | 2016 | Improvement of Nangka-Narra FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-08-31 | 100% | 4454951.93 |  | Completed
266-001-1603-G0362 | 245 | *10710020-001-0041 | 2016 | Improvement of Maninihon-Cansumalig-San Isidro FMR | Bayawan City | 5000000 | 2016-06-16 | 2017-09-15 | 100% | 4802539.95 |  | Completed
266-001-1606-G0374 | 247 | *10710020-001-0053 | 2016 | Reblocking of Concrete Pavement at Villareal-Cansumalig-San Isidro FMR, Phase 3 | Bayawan City | 500000 | 2017-03-01 | 2017-07-31 | 100% | 470136.11 |  | Completed
266-001-1603-G0364 | 249 | *10710020-001-0043 | 2016 | Reblocking of Concrete Pavement Nangka- Narra FMR | Bayawan City | 500000 | 2017-02-16 | 2017-06-30 | 100% | 472475.09 |  | Completed
266-001-1607-G0383 | 250 | *10710020-001-0062 | 2016 | Reblocking of Concrete Pavement with Slope Protection at Malabugas-San Roque Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 459598.82 |  | Completed
266-001-1606-G0373 | 251 | *10710020-001-0052 | 2016 | Reblocking of Concrete Pavement with Slope Protection at Tabuan-Banay-banay Route | Bayawan City | 500000 | 2017-05-01 | 2017-10-31 | 100% | 463537.29 |  | Completed
266-001-1606-G0370 | 252 | *10710020-001-0049 | 2016 | Concreting of Road Approaching Upper Baican Box Culvert with Slope Protection | Bugay | 1000000 | 2016-10-16 | 2017-06-30 | 100% | 974648.99 |  | Completed
266-001-1606-G0369 | 254 | *10710020-001-0048 | 2016 | Concreting of Road Approaching Nayabaan Box Culvert with Slope Protection | Bugay | 1000000 | 2016-09-16 | 2017-07-15 | 100% | 908111.85 |  | Completed
266-001-1607-G0384 | 257 | *10710020-001-0063 | 2016 | Concreting of Road Approaching Cagayon Box Culvert with Slope Protection | Banaybanay | 1000000 | 2017-01-01 | 2017-10-31 | 100% | 905886.26 |  | Completed
266-001-1607-G0382 | 258 | *10710020-001-0061 | 2016 | Concreting of Road Approaching Cabigohan Box Culvert with Slope Protection | Dawis | 1000000 | 2017-05-01 | 2017-10-15 | 100% | 790349.47 |  | Completed
266-003-1608-G0022 | 260 | 10710020-030-0001 | 2016 | Installation of Guardrails at Kalumboyan Bridge Approaches | Kalumboyan | 2000000 | 2017-08-01 | 2018-06-30 | 100% | 1737337.87 |  | Physically Completed: Consolidated Materials delivered- 82%; rebid- 18%; [lumber & plywood]
266-003-1602-G0018 | 261 | *10710020-006-0008 | 2016 | Const. Tiki Footbridge, Phase 2 Brgy. Kalumboyan | Kalumboyan | 700000 | 2017-04-16 | 2018-02-28 | 100% | 685551.67 |  | Completed
266-001-1512-G0347 | 262 | 10710020-001-0025 | 2016 | Const. of Urban Roads (Gomez to Kabankalan Road) | City Proper | 8000000 | 2017-06-01 | 2018-12-31 | 100% | 5854241.79 |  | Physically Completed
0 | 264 | 10710020-001-0032 | 2016 | Rehab of FMR at So. Pag-awitan, Ali-is | Ali-is | 500000 | 2018-05-16 | 2018-12-31 | 100% | 296371.2 |  | Physically Completed
266-001-1602-G0358 | 268 | 10710020-001-0036 | 2016 | Road Opening at Sitio Palasanon, Cansinacao, Guintalasan Mangharaw & Guinhamogan, Brgy Cansumalig | Cansumalig | 500000 | 2018-02-16 |  | 50% | 114051.44 |  | On-Going: Materials Completely Delivered
266-001-1602-G0355 | 269 | 10710020-001-0033 | 2016 | Road Rehabilitation at so. Camague, Brgy Dawis | Villareal | 500000 |  |  |  | 82591.46 |  | Pending: No available H.E. and Road not yet passable; Materials Completely Delivered
266-001-1602-G0357 | 271 | 10710020-001-0035 | 2016 | Road surfacing at Manduao-Bucao, Brgy Manduao | Manduao | 500000 | 2016-03-16 |  | 5% | 167283.93 |  | Temporarily stopped, road not yet passable.
266-003-1607-G0020 | 273 | *10710020-006-0009 | 2016 | Const. of Steel Bridge Connecting So. Malampa to So. Tab-ang, Brgy Pagatban | Pagatban | 500000 | 2017-06-16 | 2018-01-31 | 100% | 360828.1 |  | Completed
266-001-1607-G0381 | 276 | *10710020-001-0060 | 2016 | Const. or Road from Gov't. Ctr. To sitio Buli-buli/Phase 2 | Banga | 2000000 | 2017-01-01 | 11-31-17 | 100% | 1670978.21 |  | Completed
266-001-1607-G0385 | 277 | 10710020-001-0064 | 2016 | Improvement of Road Along Bayawan CIP Main Canal | Bayawan City | 190000 |  |  |  | 90000 |  | For Implementation: Consolidated Materials delivered- 100%
266-003-1607-G0021 | 278 | 10710020-006-0010 | 2016 | Const. of Footbridge at Sitio Lower Baican, Brgy Villasol | Baican, Villasol | 220000 | 2018-02-01 | 2018-06-30 | 100% | 141047.41 |  | Physically Completed: Consolidated Materials delivered- 84%; rebid- 16% [plywood & lumber]
| 279 |  |  | Artesian Wells, Reservoir, Pumping Stations & Conduits
269-001-1612-g0043 | 280 | 10710020-002-0041 | 2016 | Rehabilitation of San Isidro Water Supply System | Villareal | 350000 |  |  |  | 104295.05 |  | For Implementation: Materials delivered-92%; cancelled- 8% [g.i. pipe/ niple/ bell reducer; 100-17-11-039 g.i. pipe - for delivery]
264-009-1702-G0561 | 282 | *10710030-030-0085 | 2016 | Const. of Water Tank & Pipeline at Tabuan Brgy Proper | Tabuan | 500000 | 2017-05-01 | 2018-05-31 | 99.5% | 424113.31 |  | Completed
269-001-1608-G0041 | 283 | 10710020-002-0039 | 2016 | Construction of Tayawan Water System | Tayawan | 300000 | 2017-06-01 | 2019-02-28 | 95% | 251967.06 |  | Temporary Stopped: RCPC for water source cannot be delivered on site due to road not passable; Consolidated: Materials delivered- 80%; rebid- 20% [RCCP, plywood & lumber]
| 284 |  |  | Irrigation, Canals & Laterals
270-001-1607-G0015 | 285 | *10710020-003-0004 | 2016 | Rehabilitation of Bayawan Communal Irrigation System | Pagatban | 500000 | 2016-08-16 | 2016-12-31 | 100% | 458455.32 |  | Completed
270-001-1701-G0017 | 286 | 10710020-003-0005 | 2016 | Const. of Small Scale Irrigation Project at Sitio Magsulay, Narra | Narra | 1000000 |  |  |  | 939233.52
| 287 |  |  | Flood Controls
271-002-1607-G0038 | 288 | *10710020-007-0010 | 2016 | Construction of Drainage City Streets - Zamora, Teologio Sts, Subd Area | Zamora, Teologio & Subd Area | 3000000 | 2017-01-01 | 2017-09-15 | 100% | 2461029.39 |  | Completed
272-002-1702-G0033 | 292 | 10710020-005-0008 | 2016 | Rehabilitation of River Bank Protection at Sitio Ebuan, Nangka | Nangka | 2000000 | 2017-03-16 | 2018-12-31 | 100% | 1427978.7 |  | Physically Completed
271-001-1607-G0052 | 299 | *10710020-004-0011 | 2016 | Const. of Box Culvert in So. Candalaga, Brgy Nangka | Nangka | 500000 | 2017-03-16 | 2017-06-30 | 100% | 381385.53 |  | Completed
269-002-1607-G0032 | 300 | 10710020-002-0042 | 2016 | Construction of Spring Box at Upper Talao, Brgy San Isidro | San Isidro | 500000 | 2018-04-15 |  | 88% | 253922.18 |  | Temporarily Stopped: Road not yet passable; Consolidated Materials delivered- 89%; rebid- 8% [plywood & lumber]; cancelled-3% [mesh wire]
271-001-1706-G0057 | 301 | 10710020-004-0016 | 2016 | Const. of 1 unit Single Box Culvert Phase 1 at So, Magsakang, brgy Tayawan | Tayawan | 500000 | 2018-01-16 | 2018-05-15 | 100% | 410379.87 |  | Physically Completed: Materials Completely Delivered
271-002-1607-G0036 | 303 | *10710020-007-0011 | 2016 | Const. of Drainage Canal at along Burgos St. & AlongBollos St. Brgy Ubos | Ubos | 500000 | 2017-02-01 | 2017-06-30 | 100% | 442668.24 |  | Completed
| 304 |  |  | Waterways, Aqueducts, Seawalls, RiverWalls & Others
272-002-1609-G0032 | 305 | 10710020-005-0007 | 2016 | Rehabilitation of Riverbank @ Brgy. Nangka | Nangka | 1000000 | 2018-05-16 | 2018-12-31 | 100% | 1013905.35 |  | Physically Completed: Materials delivered- 100% (PR # 100-18-04-084)
264-002-1711-g0081/G0082 | 306 |  | 2017 | Establishment of Montessori-Type Early Child Care Development Centers | Various Brgys
| 307 | 10710030-002-0011 | 2017 | a. Establishment of Montessori-Type Early Child Care Development Centers Phase 2 | Brgy. Boyco | 2289000 | 2018-12-16 |  | 70% | 672070.52 |  | Temporarily Stopped: Non Availability of Materials, Materials delivered- 79%;for delivery- 1%; re-bid- 20%
264-002-1711-g0081/G0082 | 308 | 10710030-002-0014 | 2017 | b. Establishment of Montessori-Type Early Child Care Development Centers | Brgy. Poblacion, Bayawan City | 1211000 | 2018-01-01 | 2018-11-30 | 100% | 692536.03 |  | Physically Completed: Materials delivered- 86%; for delivery-2%; re-bid- 12%
264-009-1705-G0566 | 307 | 10710010-001-0003 | 2017 | Development of Danapa Eco Park | Nangka | 18000000 | 2016-06-12 | 2019-01-31 | 98% | 16778685.58 |  | On-Going: Contract
269-002-1704-G0035 | 308 | 10710020-030-0003 | 2017 | Development of Narra Water Park | Narra | 16000000 | 2017-09-12 | 2018-09-30 | 100% | 15993892.48 |  | Physically Completed
0 | 309 | 0 | 2017 | Development of Tabuan People's Park | Tabuan | 2000000 |  |  |  | 0
264-009-1710-G0592/G0593/g0594 | 311 | *10710030-030-0128/0129/0130 | 2017 | Construction of Coastal Park Comfort Rooms |  | 4500000 | 2018-02-15 | 2018-05-27 | 100% | 4497336 |  | Completed
| 312 | 264-009-1711-G0600 | 2017 | Construction of Children's Playground with Facilities, Ali-is | Ali-is | 500000 |  |  |  | 0 |  | for implementation
0 | 313 | 0 | 2017 | Improvement of Barangay Health Center Lying-In Clinic, Brgy. Malabugas | Malabugas | 678571.43 |  |  |  | 0
| 314 | 264-004-1711-G0033 | 2017 | Improvement of Barangay Health Center & Lying-in Clinic, Brgy. Manduao | Manduao | 100000 |  |  |  | 0 |  | for implementation
264-009-1712-g0609 | 315 | 10710030-030-0132 | 2017 | Construction of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 1728571.43 |  |  |  | 258535.71 |  | For Implementation; Amount is Obligation per SAAOB
264-009-1712-g0612 | 316 | 10710030-030-0135 | 2017 | Improvement of Evacuation Center and Multi-Purpose Building, Brgy. Poblacion | Poblacion | 878571.43 |  |  |  | 131035.71 |  | For Implementation; Amount is Obligation per SAAOB
264-002-1712-g0083 | 317 | 10710030-002-0019 | 2017 | Construction of New Day Care Center at Brgy. Poblacion | Poblacion | 800000 |  |  |  | 119250 |  | For Implementation; Amount is Obligation per SAAOB
0 | 318 | 0 | 2017 | Construction of Lying-In Clinic, Brgy. San Isidro | San Isidro | 1178571.43 |  |  |  | 0 |  | for implementation
264-004-1712-g0035 | 319 | 10710030-003-0006 | 2017 | Improvemen of Health Center and Lying-in Clinic, Brgy.San Roque | San Roque | 1678571.43 |  |  |  | 251035.71 |  | For Implementation; Amount is Obligation per SAAOB
0 | 320 | 0 | 2017 | Improvement of Barangay Health Center, Brgy. Tinago | Tinago | 600000 |  |  |  | 89250 |  | For Implementation; Amount is Obligation per SAAOB
264-009-1712-g0608 | 321 | 10710030-030-0131 | 2017 | Construction of Children's Playground with Facilities, Brgy. Villareal | Villareal | 500000 |  |  |  | 74250 |  | For Implementation; Amount is Obligation per SAAOB
0 | 322 | 0 | 2017 | Construction of Multi-Purpose Center for Senior Citizens, Brgy. Villasol | Bayawan City | 50000 |  |  |  | 0
264-004-1712-g0034 | 323 | 10710030-003-0005 | 2017 | Improvement of Barangay Health Center, Brgy. San Jose | San Jose | 60000 |  |  |  | 0 |  | for implementation
264-004-1712-g0036 | 324 | 10710030-003-0007 | 2017 | Renovation of Barangay Health Center at Brgy. Tayawan | Tayawan | 150000 |  |  |  | 64250 |  | For Implementation; Amount is Obligation per SAAOB
264-002-1712-g0084 | 325 | 10710030-002-0020 | 2017 | Renovation of Day Care Center, Brgy. Tayawan | Tayawan | 100000 |  |  |  | 14250 |  | For Implementation; Amount is Obligation per SAAOB
| 326 | 10710030-030-0049 | 2017 | Construction of Pigpens |  | 400000 |  |  |  | 3301.01
0 | 327 | 0 | 2017 | Construction of 2 Units Small Scale Rubber Processing Plant with Shed |  | 300000 |  |  |  | 0
| 328 | budget data | 2017 | Purchase of Breeding Stocks | Bayawan City | 1944000 |  |  |  | 57240 |  | For Implementation; Amount is Obligation per SAAOB
0 | 329 | 0 | 2017 | Improvement of Brgy. Dawis Livestock Auction Market | Dawis | 150000 |  |  |  | 0
264-009-1707-G0576 | 330 | *10710030-030-0091 | 2017 | Fabrication of Portable Batching Plant |  | 500000 | 2017-10-16 | 2018-05-31 | 100% | 325671.05 |  | Completed
264-009-1705-G0567 | 331 | 10710030-001-0004 | 2017 | Construction of CEO Multi-Purpose Building | Cabcabon | 2000000 | 2017-04-16 | 2019-01-31 | 99% | 1565137.99 |  | on-going
264-009-1706-g0569 | 332 | 10710030-030-0088 | 2017 | Construction of Motorpool Building at Cabcabon | Cabcabon | 8000000 | 2017-05-16 | 2019-01-31 | 97.38% | 6066821.56 |  | on-going
| 333 | no obligation | 2017 | Lot Acquisition |  | 500000 |  |  |  | 0
0 | 334 | 0 | 2017 | Establishment of Livestock Auction Market |  | 2000000 |  |  |  | 0
0 | 335 | 0 | 2017 | Improvement of Public Market Water System | Bayawan City | 500000 |  |  |  | 0
266-001-1708-g0396 | 336 | *10710020-001-0076 | 2017 | Construction of Slope Protection at Narra-Duyanduyan FMR, Sito Duyan-duyan, Brgy. Narra | Bayawan City | 1000000 | 2017-10-16 | 2018-05-31 | 100% | 895097.05 |  | Completed
271-002-1709-G0048 | 337 | 10710020-008-0006 | 2017 | Flood Control Project at Brgy. Malabugas, Phase 2 | Malabugas | 1500000 | 2017-09-01 | 2018-06-30 | 100% | 1328590.19 |  | Physically Completed
271-002-1711-g0050 | 338 | 10710020-007-0022 | 2017 | Construction of Drainage at Cabugcabugan Creek, Brgy. Poblacion, Phase 4 | Poblacion | 1356746.77 | 2017-11-16 |  | 25% | 833586.38 |  | Pending: Awaits Consultation( BMAKBI, Eldie Tinapao); Materials Delivered - 90%; For delivery - 5%: re-ad - 5%
272-002-1708-G0035 | 339 | 10710020-005-0010 | 2017 | Construction of Riverbank Protection at Camayaan Creek,Brgy. Malabugas | Malabugas | 1000000 | 2018-01-16 | 2018-10-16 | 100% | 898258.82 |  | Physically Completed
| 340 | no obligation | 2017 | Purchase of Various Agricultural Equipment | Bayawan City | 4000000
264-009-1708-G0587 | 341 | 10710030-030-0101 | 2017 | Construction of Multi-Purpose Pavement at Brgy. Ali-is | Ali-is | 580000 | 2017-12-16 | 2018-06-30 | 100% | 492259.85 |  | Physically Completed
266-003-1708-G0025 | 342 | 10710020-006-0012 | 2017 | Construction of Flat Slab Bridge at Brgy. Proper, Banaybanay | Banaybanay | 600000 | 2018-01-16 | 2018-09-30 | 100% | 480781.16 |  | Physically Completed
0 | 343 | 0 | 2017 | Improvement of FMR at Sitio Cangcawit, Banaybanay | Banaybanay | 1078571.43 |  |  |  | 0 |  | for implementation
0 | 344 | 0 | 2017 | Improvement of Covered Court & Evacuation Center, Brgy. Banga | Banga | 500000 |  |  |  | 196547.52 |  | For Implementation; Amount is Obligation per SAAOB
266-001-1708-g0401 | 345 | *10710020-001-0079 | 2017 | Improvement of FMR at Sitio Cansig-id, Brgy. Banga | Banga | 500000 | 2017-12-01 | 2018-01-31 | 100% | 445168.8 |  | Completed
0 | 346 | 0 | 2017 | Improvement of FMR from Brgy. Proper to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 |  |  |  | 0 |  | for implementation
0 | 347 | 0 | 2017 | Improvement of FMR from Brgy Proper to Sitio Canlantang,Brgy. Bugay | Bugay | 839285 |  |  |  | 0 |  | for implementation
264-009-1707-G0574 | 348 | 10710030-030-0090 | 2017 | Construction of Multi-Purpose Pavement at Sitio Guintalasan, Brgy. Cansumalig | Cansumalig | 559523.81 |  |  |  | 293822.16 |  | For Implementation: Delivered - 96%: re-ad - 4%
264-009-1708-g0579 | 349 | 10710030-030-0093 | 2017 | Construction of Multi-Purpose Pavement at Sitio Guinhamogan, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-04-18 | 2018-07-31 | 100% | 519399.55 |  | Physically Completed
264-009-1708-G0582 | 350 | 10710030-030-0099 | 2017 | Construction of Multi-Purpose Pavement at Sitio Punong, Brgy. Cansumalig | Cansumalig | 559523.81 | 2018-03-16 |  | 5% | 304093.72 |  | Temporarily stopped, road not yet passable.
| 351 | 264-009-1711-g0597 | 2017 | Construction of Satellite Farmers' Market, Brgy. Dawis | Dawis | 1000000 |  |  |  | 0
| 352 | 264-009-1711-g0595 | 2017 | Improvement of Multi-Purpose Building at Brgy. Dawis | Dawis | 678571.43 |  |  |  | 0 |  | Outsource
266-001-1708-G0394 | 353 | 10710020-001-0115 | 2017 | Improvement of FMR at Brgy. Dawis | Dawis | 150000 | 2018-06-01 | 2019-01-31 | 99% | 90294.25 |  | On-going
266-001-1708-G0405 | 354 | 10710020-001-0081 | 2017 | Improvement of Road from Barangay Proper to Kalamtukan Elementary School, Brgy. Kalamtukan | Kalamtukan | 1178571.43 | 2017-10-16 | 2018-06-15 | 100% | 1083384.59 |  | Physically Completed
264-009-1708-g0583 | 355 | 10710030-030-0100 | 2017 | Construction of Multi-Purpose Pavement at Sitio Cogon, Brgy. Kalamtukan | Kalamtukan | 500000 | 2018-01-16 | 2018-06-30 | 100% | 418405.18 |  | Physically Completed
0 | 356 | 0 | 2017 | Improvement of FMR at Brgy. Proper, Manduao | Manduao | 500000 |  |  |  | 0 |  | for implementation
269-001-1708-G0047 | 357 | 10710020-002-0047 | 2017 | Construction of Water System at Proper Manduao | Manduao | 678571.43 |  |  |  | 248499.21 |  | For Implementation: Delivered - 88%: for delivery: 8%; re-ad: 4%
264-009-1707-G0575 | 358 | 10710030-030-0089 | 2017 | Construction of Multi-Purpose Pavement at Sitio Bocaw, Manduao | Manduao | 500000 |  |  |  | 301835.2 |  | For Implementation: Delivered - 100%
269-001-1711-g0052 | 359 | 10710020-002-0052 | 2017 | Water System Development Project at Sitio Upper Camandagan, Brgy. Maninihon | Maninihon | 1000000 |  |  |  | 647344.67 |  | For Implementation: Materials Delivered - 100%
| 360 | 264-009-1712-g0606 | 2017 | Improvement of Multi-Purpose Gymnasium and Evacuation Center, Brgy. Maninihon | Maninihon | 678571.43 |  |  |  | 0 |  | Outsource
0 | 361 | 10710020-001-0114 | 2017 | Improvement of FMR at Brgy. Minaba | Minaba | 678571.43 | 2018-05-16 | 2019-01-31 | 97% | 532636.79 |  | On-going
266-001-1708-g0402 | 362 | 10710020-001-0075 | 2017 | Improvement of FMR at Sitio Kasla, Brgy. Nangka | Nangka | 1000000 | 2017-12-01 | 2018-07-31 | 100% | 877541.81 |  | Physically Completed
0 | 363 | 0 | 2017 | Establishment of Barangay Water Refilling Station, Brgy. Nangka | Nangka | 678571.43 |  |  |  | 0
0 | 364 | 10710020-001-0085 | 2017 | Improvement of FMR at Sitios Terong, Palongpong, Canggabi and Cadal-ugan, Brgy. Narra | Narra | 1000000 | 2018-05-16 |  | 20% | 205042 |  | Temporary stopped: Road not yet passable
266-001-1708-g0398 | 365 | 10710020-001-0072 | 2017 | Road Opening at Brgy. Narra Proper | Narra | 678571.43 | 2018-06-16 |  | 70% | 300509.19 |  | Temporarily Stopped: No Heavy Equipment available
0 | 366 | 10710020-002-0053 | 2017 | Installation of Water System at Brgy. Poblacion | Poblacion | 70000 | 2018-03-01 | 2018-03-15 | 100% | 28933.33 |  | Physically Completed
0 | 367 | 0 | 2017 | Construction of Barangay Public Market, Brgy. San Jose | San Jose | 1678571.43 |  |  |  | 0
0 | 368 | 0 | 2017 | Construction of Cloning Chamber at San Roque BADC | San Roque | 50000 |  |  |  | 0
264-009-1712-g0611 | 369 | 10710030-030-0134 | 2017 | Improvement of Covered Court for Evacuation Center, Brgy Suba | Suba | 1678571.43 |  |  |  | 251035.71 |  | For Implementation; Amount is Obligation per SAAOB
266-003-1704-G0023 | 370 | 10710020-006-0013 | 2017 | Improvement of Flat Slab Bridge at Sitio Magsakang, Brgy Tayawan | Tayawan | 500000 |  |  |  | 179973.07 |  | For Implementation: Delivered - 100%
266-001-1708-g0403 | 371 | 10710020-001-0074 | 2017 | Improvement of Binanigan-Guintanaan FMR, Tayawan | Tayawan | 678571.43 |  |  |  | 24776.18 |  | For Implementation: Delivered - 82%; Partial delivery = 9%: re-ad = 9%
266-001-1708-g0404 | 372 | 10710020-001-0073 | 2017 | Improvement of Binanigan-Napo FMR, Brgy. Tayawan | Tayawan | 500000 |  |  |  | 205271.33 |  | For Implementation: Delivered - 100%
| 373 | 264-009-1711-g0602 | 2017 | Improvement of Multi-Purpose Building, Brgy. Tinago | Tinago | 1128571.43 |  |  |  | 168535.72 |  | For Implementation; Amount is Obligation per SAAOB
271-002-1708-G0044 | 374 | 10710020-007-0017 | 2017 | Concreting of Drainage Canal Cover Along National Highway, Brgy. Villareal | Villareal | 678571.43 | 2017-11-16 |  | 90% | 491510.65 |  | Pending: Due to transfer of site location and Barangay & SP resolution on process
266-003-1708-G0026 | 375 | 10710020-006-0014 | 2017 | Construction of Flat Slab Bridge Connecting Barangay Proper to Purok Malinong, Brgy. Villasol | Villasol | 1078571.43 | 2018-02-15 |  | 75.05% | 680421.82 |  | On-Going
264-009-1708-G0586 | 376 | *10710030-030-0098 | 2017 | Construction of Multi-Purpose Pavement at Sitio Manghakayhakay, Brgy. Villasol | Villasol | 600000 | 2017-12-16 | 2018-03-31 | 100% | 558776.69 |  | Completed
269-001-1711-g0050 | 377 | 10710020-002-0050 | 2017 | Improvement/Rehabilitation of Water Systems for Various Barangays | Various Brgys | 934500 |  |  |  | 404504.69 |  | For Implementation: Delivered - 83%; re-ad: 17%
| 378 | 264-009-1706-G0570 | 2017 | Installation of Water Refilling Stations at Various Barangays | Various Brgys | 2200000 |  |  |  | 0 |  | for implementation
264-009-1708-g0580 | 379 | 10710030-030-0094 | 2017 | Construction of Multi-Purpose Pavement at Sitio Bolo, Brgy. Villasol | Villasol | 600000 | 2018-02-16 | 2018-06-30 | 100% | 558037.47 |  | Physically Completed
| 380 | 264-009-1712-g0605 | 2017 | Construction of Multi-Purpose Building in Barangay Tayawan | Tayawan | 900000 |  |  |  | 134996.74 |  | For Implementation; Amount is Obligation per SAAOB
0 | 381 | 0 | 2017 | Construction of Multi-Purpose Building in Barangay San Jose | San Jose | 900000 |  |  |  | 0
0 | 382 | 10710030-006-0018 | 2017 | Electrification Project for Various Barangays | Various Brgys | 10000 | 2018-06-01 | 2018-06-15 | 100% | 9060.49 |  | Physically Completed, per SAAOB
271-002-1708-G0045 | 383 | *10710020-007-0018 | 2017 | Construction of Drainage Canal at Cansumalig High School | Cansumalig | 150000 | 2017-12-16 | 2018-03-30 | 100% | 126833.17 |  | Completed
264-009-1712-g0610 | 384 | 10710010-002-0004 | 2017 | Construction of Perimeter Fence of Multi-Purpose Building, Brgy. San Miguel | San Miguel | 100000 |  |  |  | 14250 |  | For Implementation; Amount is Obligation per SAAOB
0 | 385 | 10710020-002-0086 | 2017 | Improvement of Water Systems of Guintanaan Tayawan | Tayawan | 100000 |  |  |  | 3058 |  | for implementation: Delivered 100%
269-001-1708-g0046 | 386 | 10710020-002-0046 | 2017 | Improvement of Water Systems at Manduao | Manduao | 110000 |  |  |  | 15505.76 |  | For Implementation: Delivered - 88%: for delivery: 8%; re-ad: 4%
0 | 387 | 0 | 2017 | Installation of Solar-Driven Water System for Catumbalan, Minaba | Minaba | 100000 |  |  |  | 0 |  | for implementation
264-005-1711-g0062 | 388 | 10710030-006-0015 | 2017 | Installation of Solar-Driven Water System for Oban-Oban, Brgy. Kalumboyan | Kalumboyan | 50000 |  |  |  | 10656.52 |  | For Implementation: Delivered = 80%: re-ad: 20%
0 | 389 | 0 | 2017 | Installation of Solar-Driven Water Systems for Napo, Brgy. Tayawan | Tayawan | 50000 |  |  |  | 0 |  | for implementation
0 | 390 | 0 | 2017 | Construction of Multi-Purpose Pavement at Sitio Upper Manlubid, Ali-is | Ali-is | 50000 |  |  |  | 0
264-009-1708-G0581 | 391 | 10710030-030-0095 | 2017 | Construction of Multi-Purpose Pavement at Inner Canabuan, Minaba | Minaba | 300000 | 2018-02-16 | 2018-06-30 | 100% | 260221.5 |  | Physically Completed
| 392 | 269-001-1712-g0052 | 2017 | Improvement of Water System at Sitio Pag-awitan, Brgy. Ali-is | Ali-is | 50000 |  |  |  | 35325 |  | Purchase of water meter; Materials Completely Delivered; Obligation per SAAOB
0 | 393 | 0 | 2017 | Rehabilitation and Improvement of Water System at Brgy. Banaybanay | Banaybanay | 220000 |  |  |  | 109387.5 |  | For Implementation: Delivered = 100%; Obligation per SAAOB
264-003-1712-g0022 | 394 | 10710030-004-0004 | 2017 | Improvement of Barangay Public Market, Brgy. Malabugas | Malabugas | 50000 |  |  |  | 6749.99 |  | For Implementation; Amount is Obligation per SAAOB
264-005-1711-g0063 | 395 | 10710030-006-0016 | 2017 | Installation of Electrical System in Sitio Buli-buli, Brgy. Banga | Banga | 60000 |  |  |  | 23033.64 |  | Pending: Security lights not yet deliverd; Delivered - 87%: re-ad - 13%
0 | 396 | 0 | 2017 | Installation of Electrical System in Brgy. Kalamtukan | Kalamtukan | 60000 |  |  |  | 60000 |  | For Implementation; Amount is Obligation per SAAOB
264-005-1708-G0061 | 397 | 10710030-006-0014 | 2017 | Installation of Electrical System in Brgy. Kalumboyan | Kalumboyan | 70000 |  |  |  | 26626.53 |  | For Implementation, Materials Delivered
| 398 | 269-001-1801-g0057 | 2017 | Improvement of Water System, Brgy. San Roque | San Roque | 70000 |  |  |  | 47394 |  | For Implementation: Delivered: 100%; Obligation per SAAOb
0 | 399 | 10710020-002-0054 | 2017 | Improvement of Water System, Brgy. Ubos | Ubos | 145000 | 2018-06-01 | 2018-06-15 | 100% | 136216.2 |  | Physically Completed
0 | 400 | 0 | 2017 | Improvement of Water System at Brgy. Villasol | Villasol | 70000 |  |  |  | 62346 |  | for implementation: Delivered = 100%
264-009-1708-G0584 | 401 | 10710030-030-0096 | 2017 | Construction of Multi-Purpose Pavement at Sitio Ponong, Brgy. Villasol | Villasol | 100000 |  |  |  | 51760.63 |  | Pending: Road not yet passable; Delivered - 86%; Partial delivery - 7%: re-ad - 7%
264-005-1708-G0059 | 402 | 10710030-006-0012 | 2017 | Installation of Electrical System at Sitio Malampa, Brgy. Pagatban | Pagatban | 50000 | 2018-06-01 | 2018-06-30 | 100% | 44857.31 |  | Physically Completed
0 | 403 | 0 | 2017 | Improvement of FMR at Brgy. Banaybanay | Banaybanay | 100000 |  |  |  | 0 |  | for implementation
264-005-1708-G0060 | 404 | *10710030-006-0013 | 2017 | Installation of Electrical System in Brgy. Malabugas | Malabugas | 50000 | 2018-03-16 | 2018-04-30 | 100% | 46024.73 |  | Completed
269-001-1711-g0051 | 405 | 10710020-002-0051 | 2017 | Improvement of Canabuan Water System, Brgy. Minaba | Minaba | 200000 |  |  |  | 62377.91 |  | For Implementation: Delivered = 83%: re-ad = 17%
266-001-1708-G0395 | 406 | *10710020-001-0080 | 2017 | Slope Protection at Barangay Proper, San Isidro | San Isidro | 50000 | 2017-11-16 | 2018-01-31 | 100% | 48807.67 |  | Completed
| 407 | 264-009-1711-g0596 | 2017 | Improvement of Barangay Multi-Purpose Hall, Brgy. Ali-is | Ali-is | 200000 |  |  |  | 0 |  | Contract: For Implementation
264-009-1708-G0585 | 408 | 10710030-030-0097 | 2017 | Construction of Multi-Purpose Pavement at Purok 2, Brgy. Kalamtukan | Kalamtukan | 250000 | 2018-01-16 | 2018-06-30 | 100% | 205275.02 |  | Physically Completed
266-004-1708-G0057 | 409 | *10710020-001-0071 | 2017 | Installation of Street Lights at Purok 4, Cansilong, Brgy. Malabugas | Malabugas | 100000 | 2018-03-16 | 2018-05-31 | 100% | 90521.66 |  | Physically Completed
266-001-1708-g0400 | 410 | 10710020-001-0078 | 2017 | Improvement of FMR at Sitio Napit-an, Brgy. Maninihon | Maninihon | 220000 | 2018-04-01 | 2018-07-31 | 100% | 184905.18 |  | Physically Completed
0 | 411 | 0 | 2017 | Improvement of Water System, Brgy. Minaba | Minaba | 110000 |  |  |  | 93457 |  | for implementation: Delivered = 90%: re-ad: 10%
266-001-1709-G0406 | 412 | 10710020-001-0082 | 2017 | Improvement of FMR at Sitio Ondol, Brgy. Nangka | Nangka | 100000 | 2018-04-01 | 2018-08-31 | 100% | 95011 |  | Physically Completed
0 | 413 | 0 | 2017 | Installation of Electrical System for Purok Ipil-Ipil, Brgy. San Roque | San Roque | 200000 |  |  |  | 0
266-001-1708-g0397 | 414 | *10710020-001-0077 | 2017 | Road Improvement at Brgy. Ubos | Ubos | 170000 | 2018-01-01 | 2018-02-15 | 100% | 146018.73 |  | Completed
266-001-1708-g0399 | 415 | *10710020-030-0002 | 2017 | Construction of Pathway to Banay-Banay Proper | Banay-Banay | 100000 | 2017-10-16 | 2018-02-28 | 100% | 89325.07 |  | Completed
0 | 416 | 0 | 2017 | Construction of Alternative Learning System (ALS) Building, Brgy. Kalumboyan | Kalumboyan | 200000 |  |  |  | 0 |  | by contract
266-001-1711-g0409 | 417 | 10710020-001-0084 | 2017 | Road Opening from National Highway to Purok 1 Pasil, Brgy. Malabugas | Malabugas | 150000 |  |  |  | 70424.49 |  | No ROW; Materials delivered - 100%
269-001-1707-g0045 | 418 | 10710020-002-0048 | 2017 | Installation of Deep Well at Atilano Cabangal High School, Brgy. Nangka | Nangka | 250000 |  |  |  | 10606.87 |  | Pending: re-PR due to magsaysay type deepwell not available anymore in the market; Delivered - 31%; For delivery - 4%: cancelled- 18%; re-ad - 47% (100-18-10-041 - submersible pump - for delivery)
269-001-1801-g0058 | 419 | 10710020-002-0081 | 2017 | Installation of Water System at Brgy. Pagatban | Pagatban | 50000 | 2018-03-16 | 2019-02-28 | 95% | 41977.04 |  | On-Going
266-001-1709-G0407 | 420 | 10710020-001-0083 | 2017 | Improvement of FMR at Sitio San Ramon, Brgy. Poblacion | Poblacion | 150000 | 2018-04-01 | 2018-08-31 | 100% | 143423.48 |  | Physically Completed
269-001-1707-g0044 | 421 | *10710020-002-0045 | 2017 | Improvement of Water System at Purok Dol-Dol, Brgy. San Roque | San Roque | 100000 | 2017-11-16 | 2018-01-31 | 100% | 69781.89 |  | Completed
271-002-1708-G0043 | 422 | *10710020-007-0016 | 2017 | Construction of Concrete Covered Canals, Brgy. Tinago | Tinago | 50000 | 2017-10-01 | 2017-10-31 | 100% | 46908.05 |  | Completed
271-002-1708-G0046 | 423 | *10710020-007-0019 | 2017 | Construction of Concrete Covered Canals, Brgy. Ubos | Ubos | 100000 | 2017-10-16 | 2017-11-30 | 100% | 84467.6 |  | Completed
| 424 | 264-009-1712-g0607 | 2017 | Improvement of Multi-Purpose Gym & Evacuation Center, Brgy. San Isidro | San Isidro | 495000 |  |  |  | 0
264-009-1708-g0578 | 425 | *10710030-030-0092 | 2017 | Construction of Multi-Purpose Pavement, Brgy. Dawis | Dawis | 340000 | 2017-11-01 | 2018-02-28 | 100% | 325673.96 |  | Completed
271-002-1708-G0042 | 426 | *10710020-007-0015 | 2017 | Construction of Concrete Covered Canal, Brgy. Suba | Suba | 400000 | 2017-08-16 | 2018-01-31 | 100% | 360021.69 |  | Physically Completed
| 427 | 264-009-1712-g0604 | 2017 | Construction of Multi-Purpose Building at Relocation Site, Brgy. San Miguel | San Miguel | 500000 |  |  |  | 74250 |  | For Implementation; Amount is Obligation per SAAOB
266-001-1706-g0393 | 428 | 10710020-001-0070 | 2017 | Rehabilitation of Farm to Market Road from Sitio Bosque to Tavera, Barangay Nangka | Nangka | 1000000 |  |  |  | 405000
0 | 429 | 0 | 2017 | Construction of CICL at BADC Magsulay, Barangay Narra | Narra | 1000000 |  |  |  | 0
| 430 | budget data | 2017 | Purchase of Livestock Breeding Stocks |  | 533460 |  |  | 100% | 515555.56 |  | Completed
| 431 | no obligation | 2017 | Purchase of Lot(Road Right of Way for Various Road Projects) |  | 2980124.07 |  |  |  | 0
0 | 432 | 0 | 2017 | Const. of Livelihood Center for Women at Brgy Villasol Proper |  | 100000 |  |  |  | 0
264-009-1710-G0591 | 433 | 10710030-030-0104 | 2017 | Construction of Multi-purpose Pavement at Sitio Kaayahan (Phase 1) |  | 100000 |  |  |  | 62571.46 |  | Pending: Materials delivered - 93%; for delivery - 7%
264-009-1709-G0590 | 434 | 10710030-030-0103 | 2017 | Completion of Multi-purpose Pavement at Sitio Tangistangisan |  | 330000 | 2018-02-01 | 2018-06-30 | 100% | 306358.29 |  | Physically completed
271-002-1709-G0049 | 435 | *10710020-007-0020 | 2017 | Construction of Concrete Covered Canal at Zamora St. Brgy Suba |  | 173060.9 | 2017-08-16 | 2018-01-31 | 100% | 170642.5 |  | Completed
271-002-1709-G0047 | 436 | *10710020-007-0021 | 2017 | Construction of Concrete Canal Cover Along Rizat St. Brgy Tinago |  | 1000000 | 2017-11-16 | 2018-03-31 | 100% | 678776.75 |  | Completed
| 437 |  |  | Water Supply Systems
269-001-1709-G0049 | 438 | 10710020-002-0082 | 2017 | Development of Water System at Sitio Tavera, Nangka |  | 5700000 |  |  |  | 1671861.57 |  | Materials delivered- 97%; partial delivery - 3%
| 501 | 10710020-002-0083 | 2017 | Improvement of Cabatangan-Tavera Water System |  | 154784.58 |  |  |  | 33345.9 |  | Pending: Road not yet passable; Re-Appropriated to SB # 17, 2017
| 439 |  |  | Parks, Plazas & Monuments
0 | 440 | 0 | 2017 | Improvement of Sports Center and Children's Playground, Boulevard |  | 1000000 |  |  |  | 0 |  | Outsource
| 441 |  |  | School Buildings
264-009-1709-g0589/264-002-1711-g0080/81/82 | 442 | 10710030-002-0018 | 2017 | Establishment of Early Child Development Center |  | 2300000 | 2018-03-31 |  | 70% | 2040993.3 |  | On-Going
| 443 |  |  | Other Structures
| 444 | no obligation | 2017 | Construction of Workshop Area for Bayawan City Technology & Livelihood Development Center (BCTLDC) |  | 3000000 |  |  |  | 0
| 445 |  | 2017 | Purchase of Workshop Tools and Equipment for BCTLDC:
| 446 |  | 2017 | Furniture & Fixtures
| 447 |  | 2017 | 3 units Exhaust Fan |  | 4500 |  |  |  | 4500
| 448 |  | 2017 | 3 units Industrial Fan |  | 19656 |  |  |  | 19656
| 449 |  | 2017 | 4 units White Board with Movable Stand |  | 11000 |  |  |  | 11000
| 450 |  | 2017 | 3 units White Board (4x8x3/4) |  | 9900 |  |  |  | 9900
| 451 |  | 2017 | Machinery
| 452 |  | 2017 | 18 units Arc Welding Machine AC/DC & Acc |  | 698040 |  |  |  | 698040
| 453 |  | 2017 | Communication Equipment
| 454 |  | 2017 | 1 unit LCD projector |  | 26000 |  |  |  | 22995
| 455 |  | 2017 | Disaster Response & Rescue Equipment
| 456 |  | 2017 | 4 units Fire Extinguishers |  | 12364 |  |  |  | 12364
| 457 |  | 2017 | Military, Police & Security Equipment
| 458 |  | 2017 | 1 Set Security Equipment Access Control (CCTV) |  | 29845 |  |  |  | 29845
| 460 |  | 2017 | Other Machinery & Equipment
| 461 |  | 2017 | 6 units Work Bench w/ Bench Vice on 4 Corners |  | 204000 |  |  |  | 204000
| 462 |  | 2017 | 25 sets Combination Spanner (6mm to 24 mm) |  | 80000 |  |  |  | 80000
| 463 |  | 2017 | 12 units Blow Torch |  | 18000 |  |  |  | 18000
| 464 |  | 2017 | 12 units Clamp on Meter |  | 36000 |  |  |  | 36000
| 465 |  | 2017 | 6 units Portable Electric Drill |  | 30000 |  |  |  | 30000
| 466 |  | 2017 | 6 units Portable Planer |  | 51600 |  |  |  | 51600
| 467 |  | 2017 | 6 units Portable Circular Saw |  | 47220 |  |  |  | 47220
| 468 |  | 2017 | 25 pcs Welding Positioners |  | 96250 |  |  |  | 96250
| 469 |  | 2017 | 6 units Electrode Oven |  | 24000 |  |  |  | 24000
| 470 |  | 2017 | 25 units Portable Disc Grinder |  | 78750 |  |  |  | 78750
| 471 |  | 2017 | 6 units Pipe Threader 1/2-2" |  | 343200 |  |  |  | 343200
| 472 |  | 2017 | 6 units Pipe Bender |  | 26400 |  |  |  | 26400
| 473 |  | 2017 | 6 units Heat Gun 1200 watts |  | 18900 |  |  |  | 18900
| 474 |  | 2017 | 6 units Bolt Cutter |  | 7680 |  |  |  | 7680
| 475 |  | 2017 | 12 pcs Box Wrench |  | 58800 |  |  |  | 58800
| 476 |  | 2017 | 12 pcs Wire Splicer |  | 25320 |  |  |  | 25320
| 477 |  | 2017 | 12 pcs Wire Stripper |  | 25320 |  |  |  | 25320
| 478 |  | 2017 | 12 units Electric Drill |  | 58800 |  |  |  | 58800
| 479 |  | 2017 | 12 units Portable Grinder |  | 52500 |  |  |  | 52500
| 480 |  | 2017 | 6 units Pipe Cutter (1/2"-1") |  | 31590 |  |  |  | 31590
| 481 |  | 2017 | 3 units Manual Pipe Threader (1/2", 3/4", 1") |  | 33705 |  |  |  | 33705
| 482 |  | 2017 | 3 units Fusion Machine (20mm-32mm) |  | 34020 |  |  |  | 34020
| 483 |  | 2017 | 4 units Electric Grinder (4") |  | 20520 |  |  |  | 20520
| 484 |  | 2017 | 12 units Angle Grinder |  | 61560 |  |  |  | 61560
| 485 |  | 2017 | 2 units Labelling Machine |  | 2200 |  |  |  | 2200
| 486 |  | 2017 | 6 units Insulation Resistance Tester |  | 9900 |  |  |  | 9900
| 487 |  | 2017 | 6 units Earth Resistance Tester |  | 13200 |  |  |  | 13200
| 488 |  | 2017 | 4 units Pedestal/Bench Grinding Machine |  | 9400 |  |  |  | 9400
| 489 |  | 2017 | 10 units Panel Board with 70 amp main & 4 |  | 34450 |  |  |  | 34450
| 490 |  | 2017 | 25 pcs Electrician Pliers |  | 66250 |  |  |  | 66250
| 491 |  | 2017 | Other Property, Plant & Equipment
| 492 |  | 2017 | 3 units Wheelbarrow |  | 6600 |  |  |  | 6600
| 493 |  | 2017 | 6 sets Oxy-Acetylene/Oxy-LPG Cutting Outfit |  | 72000 |  |  |  | 72000
| 494 |  | 2017 | 6 units Plastic Drum (200 liters) |  | 10560 |  |  |  | 10560
495
| 496 |  |  | Power Supply System
| 497 |  | 2017 | Purchase of 50 KVA Transformer for BCTLDC |  | 500000 |  |  |  | 0
| 498 |  |  | Hospital and Health Centers
| 499 |  | 2017 | Construction of City Health Office Building |  | 1000000
| 7 |  | 2018 | Lot Acquisition for Development Projects |  | 1754285.71 |  |  |  | 0
| 8 |  | 2018 | Purchase of Lot for Multi-Purpose Hall at Sitio Cambulo. Banga |  | 600000 |  |  |  | 0
| 9 | 10710020-001-0112 | 2018 | Widening of Malabugas-San Roque Road |  | 3500000 |  |  |  | 507870.31 |  | Pending: Lack of Heavy Equipment; For re-bid schedule
| 10 | 10710020-001-0095 | 2018 | Concreting of Road Approaching Lapay Box Culvert with Slope Protection, Dawis | Bayawan Creek, Dawis | 1000000 | 2018-04-01 | 2018-08-31 | 100% | 508049.24 |  | Physically Completed
| 11 | 10710020-001-0094 | 2018 | Concreting of Road Approaching Candalaga Box Culvert with Slope Protection, Nangka | Nangka | 1000000 | 2018-04-01 | 2018-11-30 | 100% | 656944.68 |  | Physically Completed
| 12 | 10710020-001-0098 | 2018 | Concreting of Road Approaching Pusi-on Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2019-01-31 | 98% | 456300.06 |  | Temporarily stopped: Road not yet passable
| 13 | 10710020-001-0093 | 2018 | Concreting of Road Approaching Camandagan Box Culvert with Slope Protection, Maninihon | Maninihon | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 433092.23 |  | Physically Completed
| 14 | 10710020-001-0091 | 2018 | Concreting of Road Approaching Balao Box Culvert with Slope Protection, San Miguel | San Miguel | 1000000 | 2018-04-01 | 2018-10-30 | 100% | 465259.71 |  | Physically Completed
| 15 | 10710020-001-0096 | 2018 | Concreting of Road Approaching Magsakang Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 |  | 18% | 152633.74 |  | Pending: Road not yet passable
| 16 | 10710020-006-0016 | 2018 | Completion of Magsakang Flat Slab Bridge, Tayawan | Tayawan | 1000000 | 2018-04-01 |  | 80% | 623621.79 |  | On-Going
| 17 | 10710020-001-0097 | 2018 | Concreting of Road Approaching Pamuat Box Culvert with Slope Protection, San Isidro | San Isidro | 1000000 | 2018-04-01 |  | 7% | 145174.05 |  | On-Going
| 18 | 10710020-001-0092 | 2018 | Concreting of Road Approaching Binanigan Box Culvert with Slope Protection, Tayawan | Tayawan | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 394116.75 |  | Physically Completed
| 19 | 10710020-001-0086 | 2018 | Concreting of Road at Purok 7, Barangay Tinago | Tinago | 2000000 | 2018-02-16 | 2018-08-31 | 100% | 1714331.49 |  | Physically Completed
| 20 | 10710020-001-0088 | 2018 | Concreting of Dawis-Lapay FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-03-31 | 90% | 2718880.94 |  | On-Going
| 21 | 10710020-001-0087 | 2018 | Concreting of Banga-San Roque-Minaba-San Miguel-Tayawan FMR | Bayawan City | 5872000 | 2018-04-01 | 2019-02-28 | 96% | 3031091.6 |  | On-Going
| 22 | 10710020-001-0090 | 2018 | Concreting of Nangka-Narra FMR | Bayawan City | 5500000 | 2018-04-01 | 2019-03-31 | 90% | 3011735.2 |  | On-Going
| 23 | 10710020-001-0105 | 2018 | Concreting of Tabuan- Banaybanay-Lapay-Bugay-San Jose-Manduao FMR | Bayawan City | 28340000 | 2018-05-29 |  | 40% | 7724838.4 |  | On-Going
| 24 | 10710020-001-0103 | 2018 | Concreting of Road from Sitio Balastro to Sitio Candulion to Pulangyuta, Barangay Kalamtukan | Kalamtukan | 10500000 | 2018-08-01 |  | 7.32% | 1484552.61 |  | On-Going
| 25 | 10710020-001-0104 | 2018 | Concreting of Road with Drainage Canal at Upper Napit-an, Maninihon | Maninihon | 300000 | 2018-04-01 | 2018-07-31 | 100% | 141538.64 |  | Physically Completed
| 26 | 10710020-001-0102 | 2018 | Concreting of Road from Highway Intersection to Minaba Elem. School, Brgy. Minaba | Bayawan City | 1000000 | 2018-04-01 | 2018-09-30 | 100% | 506703.12 |  | Physically Completed
| 27 | 10710020-001-0099 | 2018 | Concreting of Road at Sitio Kasla, Brgy. Nangka | Nangka | 850000 | 2018-04-01 | 2018-09-30 | 100% | 336057.36 |  | Physically Completed
| 28 | 10710020-006-0020 | 2018 | Construction of Flat Slab Bridge at Sitio Terong, Narra | Narra | 600000 | 2018-04-01 | 2018-03-31 | 70% | 402912.51 |  | On-Going
| 29 | 10710020-001-0107 | 2018 | Road Concreting from Proper Narra to Purok III, Brgy. Narra | Narra | 500000 | 2018-04-01 | 2018-10-16 | 100% | 245436.08 |  | Physically Completed
| 30 | 10710020-001-0089 | 2018 | Concreting of FMR from National Highway to Sitio Lapacon, Brgy. Pagatban | Bayawan City | 500000 | 2018-04-01 | 2018-08-31 | 100% | 198838.29 |  | Physically Completed
| 31 | 10710020-001-0100 | 2018 | Concreting of Road at Sitio Upper Pamu-at, San Isidro | San Isidro | 500000 | 2018-04-01 |  | 4% | 91627.17 |  | Pending: Road not yet passable
| 32 | 10710020-001-0101 | 2018 | Concreting of Road at Upper Talao, San Isidro | San Isidro | 600000 | 2018-10-01 | 2019-01-31 | 98% | 272885.05 |  | On-Going
| 33 | 10710020-001-0108 | 2018 | Road Shouldering Along Zamora St., Brgy. Ubos | Ubos | 500000 | 2018-06-16 | 2018-11-30 | 100% | 202182.31 |  | Physically Completed
| 34 | 10710020-001-0110 | 2018 | Road Surfacing from Barangay Proper to Sitio Gawgaw to Sitio Aya, Brgy. Bugay | Bugay | 839286.43 |  |  |  | 90199.79 |  | For Implementation: Materials delivered- 83%; for delivery- 14%; re-bid- 3%
| 35 | 10710020-001-0111 | 2018 | Road Surfacing from Barangay Proper to Sitio Mambuy-og to Sitio Canlantang, Brgy. Bugay | Bugay | 839285 |  |  |  | 88544.82 |  | Pending: Road not yet passable; Materials delivered- 83%; for delivery- 14%; re-bid- 3%
| 36 | 10710020-001-0109 | 2018 | Road Surfacing from Barangay Cansumalig | Cansumalig | 1078571.43 |  |  |  | 114560.63 |  | Pending: Road not yet passable; Materials delivered- 83%; for delivery- 17%
| 37 | 10710020-007-0026 | 2018 | Construction of Drainage Canal from Upper Napit-an to Lower Napit-an, Brgy. Maninihon | Maninihon | 650000 | 2018-06-01 | 2018-09-30 | 100% | 397366.58 |  | Physically Completed
| 38 | 10710020-004-0017 | 2018 | Installation of Cylindrical Culvert with Riprap at Proper Narra | Narra | 578571.43 | 2018-06-16 |  | 85% | 426881.04 |  | On-Going
| 39 | 10710020-007-0025 | 2018 | Covering of Drainage Canals along Gomez St., Brgy. Ubos | Ubos | 1078571.43 |  |  |  | 287139.05 |  | C/o GSO: Materials delivered- 85%; for delivery- 15%
| 40 |  | 2018 | Construction of Small Scale Irrigation Projects (SSIP): | Bayawan City
| 41 | 10710020-003-0007 | 2018 | a. Purok Mangga, Brgy. Manduao | Manduao | 800000 |  |  |  | 127311.89 |  | for implementation: Materials delivered- 83%; for delivery-13%: re-ad - 4%
| 42 | 10710020-003-0008 | 2018 | b. Sitio Dita, Brgy. Tabuan | Tabuan | 800000 |  |  |  | 189891.39 |  | for implementation: Materials delivered- 80%; for delivery- 15%; re-bid- 5%
| 43 | 10710020-003-0009 | 2018 | c. Upper Canlinte, Brgy Ali-is | Ali-is | 800000 |  |  |  | 173990.61 |  | for implementation: Materials delivered- 72%; for delivery- 14%; re-bid- 14%
| 44 | 10710020-003-0010 | 2018 | Rehabilitation of Irrigation Canal at Brgy. Tabuan | Tabuan | 915000 |  |  |  | 263178.2 |  | For Implementation: Materials delivered- 81%; for delivery- 19%
| 45 | 10710020-002-0057 | 2018 | Water System Development at Bugay Proper | Bugay | 500000 |  |  |  | 136524.8 |  | For Implementation: Materials for delivery- 66%; re-ad- 34%
| 46 | 10710020-002-0056 | 2018 | Development of Water System at Brgy. Villareal | Villareal | 1000000 |  |  |  | 327600 |  | For Implementation: Materials delivered- 55%; re-bid- 45%
| 47 | 10710020-001-0113 | 2018 | Installation of Street Lighting from Purok 1 to Purok IV, Brgy. Tayawan | Tayawan | 500000 |  |  |  | 127121.21 |  | For Implementation: Materials delivered- 82%; partial delivery - 4%; for delivery- 7%; re-bid- 7%
| 48 | 10710020-009-0001 | 2018 | Improvement of Barangay Plaza and Children's Park, Tayawan | Tayawan | 500000 |  |  |  | 0 |  | For Implementation
| 49 |  | 2018 | Establishment of Early Child Care Dev't Centers: | Bayawan City
| 50 | 10710030-002-0021 | 2018 | a. Brgy. Villareal | Villareal | 5000000 |  |  |  | 20850.19 |  | For Implementation
| 51 | 10710030-002-0022 | 2018 | b. Brgy. Malabugas | Malabugas | 5000000 | 2018-06-21 |  | 55% | 2197139.64 |  | On-Going
| 52 | 10710030-002-0023 | 2018 | Construction of Day Care Center at Sitio Mantapi, Nangka | Nangka | 578571.43 |  |  |  | 271305.65 |  | C/O GSO; Materials delivered- 85%; for delivery- 15%
| 53 | 0 | 2018 | Improvement of Barangay Health Center & Lying-In Clinic, Brgy. Malabugas | Malabugas | 1000000 |  |  |  | 0 |  | For Implementation
| 54 | 10710030-003-0008 | 2018 | Construction of Health Center at Sitio Mantapi, Nangka | Nangka | 500000 |  |  |  | 110023.07 |  | C/o GSO: Materials delivered- 100%
| 55 | 0 | 2018 | Construction of Barangay Public Market, Ali-is (Phase 1) | Bayawan City | 1000000 |  |  |  | 0 |  | For Implementation
| 56 | 10710030-005-0001 | 2018 | Completion of Minaba Mini Slaughterhouse Phase III | Minaba | 500000 | 2018-10-16 |  | 50% | 197427.01 |  | On-Going
| 57 |  | 2018 | Construction of Rainwater Harvesting Systems for Nurseries:
| 58 | 10710020-002-0075 | 2018 | a. Brgy. San Miguel | San Miguel | 250000 | 2018-10-01 | 2018-11-30 | 100% | 153081.97 |  | Physically Completed
| 59 | 10710020-002-0076 | 2018 | b. Brgy. Tayawan | Tayawan | 250000 | 2018-10-16 | 2019-02-28 | 90% | 70503.11 |  | On-Going
| 60 | 10710020-002-0077 | 2018 | c. Brgy. Cansumalig | Cansumalig | 250000 | 2018-10-16 | 2018-03-31 | 90% | 108874.5 |  | On-Going: Materials delivered- 77%; for delivery- 7%; re-bid- 16%
| 61 | 10710020-002-0078 | 2018 | d. Brgy. Manduao | Manduao | 250000 |  |  |  | 42251.8 |  | For Implementation: Materials delivered- 77%; for delivery- 7%; re-bid- 16%
| 62 | 10710020-002-0079 | 2018 | e. Brgy. Kalamtukan | Kalamtukan | 250000 |  |  |  | 104730.6 |  | For Implementation: Materials delivered - 98%; cancelled - 2%
| 63 | 10710030-030-0138 | 2018 | Construction of Bleachers at Barangay Evacuation Center, Ali-is | Ali-is | 678571.43 | 2018-04-01 | 2019-01-31 | 98.5% | 464269.57 |  | On-Going
| 64 | 10710030-030-0146 | 2018 | Improvement of Barangay Multi-Purpose Building, Banaybanay | Banaybanay | 1000000 |  |  |  | 0 |  | For Implementation
| 65 | 10710030-030-0150 | 2018 | Improvement of Barangay Multi-Purpose Hall, Brgy. Boyco | Boyco | 1678571.43 |  |  |  | 0 |  | For Implementation
| 66 | 10710030-030-0144 | 2018 | Construction of Barangay Multi-Purpose Building, Cansumalig | Cansumalig | 1300000 |  |  |  | 0 |  | For Implementation
| 67 | 10710030-002-0024 | 2018 | Construction of Feeding Center at Damig Elementary School, Brgy. Kalamtukan | Kalamtukan | 778571.43 |  |  |  | 0 |  | Contract: For Implementation
| 68 | 10710030-030-0147 | 2018 | Improvement of Barangay Multi-Purpose Building, Maninihon | Maninihon | 1000000 |  |  |  | 0 |  | For Implementation
| 69 | 10710030-030-0155 | 2018 | Construction of Multi-Purpose Pavement at Sitio Mantapi, Nangka | Mantapi, Nangka | 600000 | 2018-07-01 | 2018-12-31 | 100% | 489270.51 |  | Physically Completed
| 70 | 10710030-030-0148 | 2018 | Construction of Barangay Multi-Purpose Building, Narra | Narra | 1000000 |  |  |  | 0 |  | For Implementation
| 71 | 10710010-002-0005 | 2018 | Construction of Concrete Perimeter Fence of Covered Court and Evacuation Center, Brgy. Pagatban | Pagatban | 100000 | 2018-07-01 | 2018-08-31 | 100% | 73114.46 |  | Physically Completed
| 72 | 10710030-030-0145 | 2018 | Construction of Multi-Purpose Building, Brgy. San Isidro (Phase 2) | San Isidro | 1078571.43 |  |  |  | 0 |  | For Implementation
| 73 | 10710030-030-0137 | 2018 | Construction of Children and Women's Crisis Center, Brgy. Suba | Suba | 600000 |  |  |  | 0 |  | For Implementation
| 74 | 10710030-030-0153 | 2018 | Improvement of Multi-Purpose Hall, Brgy. Suba | Suba | 578571.43 |  |  |  | 0 |  | For Implementation
| 75 | 10710030-030-0149 | 2018 | Construction of Multi-Purpose Hall, Brgy. Tinago | Tinago | 2278571.43 |  |  |  | 0 |  | For Implementation
| 76 | 10710030-030-0159 | 2018 | Construction of Fish Processing Center @ Brgy. Suba | Suba | 2500000 |  |  |  | 999685.45 |  | C/O GSO; Materials delivered- 90%; for delivery- 9%; re-bid- 1%
| 77 | 10710030-030-0152 | 2018 | Improvement of Multi-Purpose Hall, Banga | Banga | 2078571.43 |  |  |  | 0 |  | For Implementation
| 78 | 10710030-030-0161 | 2018 | Major Repair of Narra Barangay Agricultural Development Center (BADC) | Narra | 520000 |  |  |  | 110457.7 |  | C/O GSO; Materials delivered- 98%; re-bid- 2%
| 79 | 10710030-030-0160 | 2018 | Major Repair of Manduao Barangay Agricultural Development Center (BADC) | Manduao | 290000 |  |  |  | 18457.71 |  | C/O GSO; Materials delivered- 96%; for delivery- 4%
| 80 | 10710030-030-0151 | 2018 | Improvement of Barangay Multi-Purpose Hall, Manduao | Manduao | 600000 |  |  |  | 0 |  | For Implementation
| 81 | no obligation | 2018 | Purchase of Boom Truck | Bayawan City | 1600000 |  |  |  | 0
| 82 |  | 2018 | Purchase of 1 Unit Backhoe for Barangay Tayawan | Tayawan | 1678571.43 |  |  |  | 0
| 83 |  | 2018 | Purchase of Garbage Compactor Truck | Bayawan City | 1500000 |  |  |  | 0
| 84 | 10701010-001-0129 | 2018 | Purchase of Lot for Agricultural Research Center | Maninihon | 16000000 |  |  | 100% | 15710989 |  | Site-Napit-an, Brgy. Maninihon; TD No. 2016-04-0013-02364;
| 85 |  | 2018 | Establishment of Agricultural Research Center | Maninihon | 6895568.71 |  |  |  | 0
| 86 |  | 2018 | Improvement of Bugay-San Jose-Manduao FMR | Bayawan City | 3000000 | 2018-10-15 | 2019-03-31 | 85% | 1763084.7 |  | On-Going
|  |  | 2018 | Concreting of Urban Roads with Drainage System (GomeZ St.) | Poblacion | 12885436.16
| 502 |  | TOTAL EDF CONTINUING APPROPRIATION |  |  | 475936032.13 |  |  |  | 242532804.77
| 503 |  | TOTAL EDF - CURRENT & CONTINUING APPROPRIATION |  |  | 676523167.13 |  |  |  | 282345860.96
|  |  |  | CORAZON P. LIRAZAN, CPA | [5 empty] | HON. PRYDE HENRY A. TEVES
|  |  |  | City Accountant | [5 empty] | City Mayor